## Instructions
Introduction
Welcome to Risk Guardian Risk Register! This register is free to use and can be modified to fit your organizations needs. Below are instructions on how to expand or modify the register.
Data Controls
All of the Drop Down lists on the Risk Register sheet are controlled by the lists on the Data Controls sheet. You can modify any of these names and they will automatically update on the Risk Register. If you need to expand the possibilities, then you will need to redo the data validation. You can find a tutorial on data validation at https://www.youtube.com/watch?v=YcTJbMJlMBQ
Calculations for Priority
The calculations for priority are based on the Risk Matrix. On the Risk Register sheet, there are hidden columns (N,O, and P) that calculate the mathematical values which are then set in the Priority column. You will need to unhide these if you want to tinker with values.
Risk ID
The Risk ID iwill fill in automatically. If you need more IDs as you expand your risk register, use the data fill option to fill down and the next ID will generate.

## Risk Register
Risk Register
ID | Date Identified | Risk Name | Risk Description | Priority | Category | Probability | Impact | Action | Strategy | Residual | Status | Owner | Probability Calc | Impact Calc | Priority
GRC001 | 2022-02-10 | Weak Login Security | Users are able to log in to critical systems using only a username and password, presenting a risk that outside actors could compromise our systems by stealing this "what you know" data. | CRITICAL | Security | 5 - Certain (>75% Chance) | 5 - Catastrophic | Implement two-factor autnetication to provide a "what you have" element to the login, preventing anyone from logging in with just a username and password. | Mitigate | No additional risk identified. | Resolved | Disaster Recovery | 5 | 5 | 25
GRC002 | 2022-05-22 | No Redundancy for Email Server | The company's exchange server is a single point of failure. If it crashes, then we would not have email until it could be brought back up or rebuilt. | HIGH | Operational | 3 - Possible (25%-50% Chance) | 5 - Catastrophic | Create additional email servers and set failover tolerances | Mitigate | Power outages or network outages at our facility could still result in outages of email. We may wish to look into a cloud provider. | In Progress | IT Ops | 3 | 5 | 15
GRC003 | 2022-05-22 | No Contract Audits | Audits are not currently being performed on contracts. This could cause failure of critical SOX compliance and result in government fines. | HIGH | Legal | 4 - Likely (51%-75% Chance) | 4 - Major |  | Mitigate | No additional risk identified. | Assessed | Legal | 4 | 4 | 16
GRC004 | 2023-06-13 | No Onboarding Process | A lack of an onboarding process means it takes longer for new employees to get all required access, equipment, and knowledge needed to be fully functional employees, resulting in lost revenue and efficiency. | CRITICAL | Financial | 5 - Certain (>75% Chance) | 4 - Major | HR will monitor the amount of time it takes an employee to become effectiive by providing employee surveys and followups for the first two months of an employee's onboarding and will advice of further strategies after results are in. | Monitor |  | In Progress | HR | 5 | 4 | 20
GRC005 | 2023-10-01 | Warehouse Theft | The warehouse where our products are stored is lacking in security cameras. This could mean we have no way to track theft from the warehouse. | MEDIUM | Financial | 3 - Possible (25%-50% Chance) | 2 - Minor | Security will hire an outside vendor to install cameras and provide 24x7 monitoring. | Transfer |  |  | Physical Security | 3 | 2 | 6
GRC006 |  |  |  | #VALUE! | Security |  |  |  | Mitigate |  |  | Disaster Recovery | #VALUE! | #VALUE! | #VALUE!
GRC007 |  |  |  | #VALUE! | Security |  |  |  | Mitigate |  |  | Disaster Recovery | #VALUE! | #VALUE! | #VALUE!
GRC008 |  |  |  | #VALUE! | Security |  |  |  | Mitigate |  |  | Disaster Recovery | #VALUE! | #VALUE! | #VALUE!
GRC009 |  |  |  | #VALUE! | Security |  |  |  | Mitigate |  |  | Disaster Recovery | #VALUE! | #VALUE! | #VALUE!
GRC010 |  |  |  | #VALUE! | Security |  |  |  | Mitigate |  |  | Disaster Recovery | #VALUE! | #VALUE! | #VALUE!
GRC011 |  |  |  | #VALUE! | Security |  |  |  | Mitigate |  |  | Disaster Recovery | #VALUE! | #VALUE! | #VALUE!
GRC012 |  |  |  | #VALUE! | Security |  |  |  | Mitigate |  |  | Disaster Recovery | #VALUE! | #VALUE! | #VALUE!
GRC013 |  |  |  | #VALUE! | Security |  |  |  | Mitigate |  |  | Disaster Recovery | #VALUE! | #VALUE! | #VALUE!
GRC014 |  |  |  | #VALUE! | Security |  |  |  | Mitigate |  |  | Disaster Recovery | #VALUE! | #VALUE! | #VALUE!
GRC015 |  |  |  | #VALUE! | Security |  |  |  | Mitigate |  |  | Disaster Recovery | #VALUE! | #VALUE! | #VALUE!
Note on A2: Matthew Stephens: The ID number will be autogenerated if you use the fill down to drag down to the next space.

## Risk Matrix
Risk Matrix
Impact | Negligible | Minor | Moderate | Major | Catastrophic
Rare | Low | Low | Low | Medium | Medium
Unlikely | Low | Low | Medium | Medium | High
Possible | Low | Medium | Medium | High | High
Likely | Medium | Medium | High | High | Critical
Certain | Medium | High | High | Critical | Critical

## Data Controls
Category | Probability | Impact | Strategy | Status | Owner
Operational | 1 - Rare (Extremely Unlikely) | 1 - Negligible | Avoid | Identified | Cybersecurity
Financial | 2 Unlikely (<25% Chance) | 2 - Minor | Mitigate | Assessed | IT Ops
Technical | 3 - Possible (25%-50% Chance) | 3 - Moderate | Transfer | In Progress | Legal
Legal | 4 - Likely (51%-75% Chance) | 4 - Major | Accept | Escalated | Risk Mgmt
Compliance | 5 - Certain (>75% Chance) | 5 - Catastrophic | Share | Monitoring | HR
Security |  |  | Monitor | Resolved | Finance
Executives
Disaster Recovery
Product
Vendor
IA
Marketing
Physical Security